## 1
identification | title | category | start_state
case-1 | Parks Canada, Trent Severn Waterway, Dam at Lock 23 Replacement | Medium | begin-case-1
identification | type | title | date | event | actors | input_items | output_items | route | route_completed | alternate_routes | alternate_routes_completed
begin-case-1 | BEGIN | Begin case | [5 empty] | authorization-issuance-case-1 | Y
authorization-issuance-case-1 | ACTION | Authorization issued on November 9, 2018. | 2018-11-09 |  |  | Case application | Serious Harm associated with phase 1 cofferdam footprint and dewatering – 2417 m2 November 1, 2018 to July 15, 2019¦Serious Harm associated with phase 2 cofferdam footprint and dewatering – 1867 m2 July 15, 2019 to July 15 2020¦ Serious Harm associated with 1088 m2 of infill associated with moving the dam downstream¦Fourteen conditions relating to avoiding and mitigating serious harm¦6 contingency measures | monitoring-report-process-case-1 | Y
monitoring-report-process-case-1 | PROCESS | Monitoring and report for avoidance and mitigation | 2018-11-09 |  |  |  |  | begin-monitoring-report-case-1 | Y
begin-monitoring-report-case-1 | BEGIN | Begin monitoring and report for avoidance and mitigation | 2018-11-09 |  |  | Fourteen conditions relating to avoiding and mitigating serious harm¦6 contingency measures | Habitat enhancement - creating a Walleye spawning shoal (760m2) at an offsite location¦ Reinstating 1080m2 of habitat upstream of the dam¦ 5 criteria to assess the implementation and effectiveness of the measures | report-1-case-1 | Y | site-visit-case-1 | Y
site-visit-case-1 | ACTION | DFO site visit | 2019-10-29 |  |  |  |  | report-1-case-1 | Y
report-1-case-1 | INPUT | Interim report 1 on effectiveness |  | 2019-12-31 | Parks Canada |  | Interim report 1 | receive-report-1-case-1 | Y
receive-report-1-case-1 | DECISION | Report received | 2019-11-29 | 2019-11-29 |  | Interim report 1 | Verified interim report 1 | report-2-case-1 | Y
report-2-case-1 | INPUT | Interim report 2 on effectiveness |  | 2020-12-31 | Parks Canada |  | Interim report 2 | receive-report-2-case-1 | Y
receive-report-2-case-1 | DECISION | Report received | 2020-12-22 | 2020-12-22 |  | Interim report 2 | Verified interim report 2 | report-3-case-1 | Y
report-3-case-1 | INPUT | Final report on effectiveness |  | 2021-12-31 | Parks Canada |  |  | decision-monitoring-report-case-1 | N
decision-monitoring-report-case-1 | DECISION | Decision for monitoring report |  |  |  | All monitoring reports | All verified monitoring reports | end-monitoring-report-case-1 | N
end-monitoring-report-case-1 | END | End monitoring and report for avoidance and mitigation | 2018-11-09 |  |  |  |  | end-case-1 | N
end-case-1 | END | End case | 2018-11-09
Note on G4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on H4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on J4: Nghia Doan: Already exists (Y) or placeholder for future (N)
Note on K4: Nghia Doan: Additional states to be connected to
Note on L4: Nghia Doan: Already exists (Y) or placeholder for future (N)