## 1
Identification | Title | Category
case-1 | Parks Canada, Trent Severn Waterway, Dam at Lock 23 Replacement | Medium
Identification | Type | Title | Date | Event | Actor | Input Items | Execution Condition | Output Items | Routing Condition | Existing | Also connected to | Existing
begin-case-1 | BEGIN | Begin case | [6 empty] | authorization-issuance-case-1 | Y |  | Y
authorization-issuance-case-1 | ACTION | Authorization issued on November 9, 2018. | 2018-11-09 |  | Hydro and Flows Regulatory Review | Case application |  | Serious Harm associated with phase 1 cofferdam footprint and dewatering – 2417 m2 November 1, 2018 to July 15, 2019¦Serious Harm associated with phase 2 cofferdam footprint and dewatering – 1867 m2 July 15, 2019 to July 15 2020¦ Serious Harm associated with 1088 m2 of infill associated with moving the dam downstream¦Fourteen conditions relating to avoiding and mitigating serious harm¦6 contingency measures | monitoring-report-process-case-1 | Y |  | Y
monitoring-report-process-case-1 | PROCESS | Monitoring and report for avoidance and mitigation |  |  | Hydro and Flows Regulatory Review |  |  |  | begin-monitoring-report-case-1 | Y | end-case-1 | N
begin-monitoring-report-case-1 | BEGIN | Begin monitoring and report for avoidance and mitigation |  |  | Hydro and Flows Regulatory Review | Fourteen conditions relating to avoiding and mitigating serious harm¦6 contingency measures |  | Habitat enhancement - creating a Walleye spawning shoal (760m2) at an offsite location¦ Reinstating 1080m2 of habitat upstream of the dam¦ 5 criteria to assess the implementation and effectiveness of the measures | decision-report-case-1 | Y | site-visit-case-1 | Y
site-visit-case-1 | ACTION | DFO site visit | 2019-10-29 |  | Hydro and Flows Regulatory Review |  |  |  | decision-report-case-1 | Y |  | Y
report-1-case-1 | INPUT | Interim report 1 on effectiveness |  | December 31, 2019 | Proponent |  |  | Monitoring report | receive-report-1-case-1 | Y |  | Y
receive-report-1-case-1 | DECISION | Report received |  | November 29, 2019 | Hydro and Flows Regulatory Review | Monitoring report | Report received | Verified monitoring report | report-2-case-1 | Y |  | Y
report-2-case-1 | INPUT | Interim report on effectiveness |  | December 31, 2020 | Proponent |  |  | Monitoring report | receive-report-2-case-1 | Y |  | Y
receive-report-2-case-1 | DECISION | Report received |  | December 22, 2020 | Hydro and Flows Regulatory Review | Monitoring report | Report received | Verified monitoring report | report-2-case-1 | Y |  | Y
report-3-case-1 | INPUT | Final report on effectiveness |  | December 31, 2021 | Proponent |  |  |  | report-3-case-1 | N |  | N
decision-monitoring-report-case—1 | DECISION | Decision for monitoring report |  |  | Hydro and Flows Regulatory Review | All monitoring reports | All monitoring reports received |  | end-monitoring-report-case-1 | N |  | N
end-monitoring-report-case-1 | END | End monitoring and report for avoidance and mitigation | [6 empty] | monitoring-report-process-case-1 | N |  | N
end-case-1 | END | End case
Note on H4: Nghia Doan: It enables execution of the state
Note on I4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on J4: Nghia Doan: Among the states following the current one, which ones should be activated? It can be: - no condition, the single next state should be activated - identification of a single chosen state (among many others) - true/false or multiple choice values for following states
Note on L4: Nghia Doan: Additional states to be connected to