## 1
identification | title | category | start_state
case-1 | Parks Canada, Trent Severn Waterway, Dam at Lock 23 Replacement | Medium | begin-case-1
identification | type | title | date | event | actors | input_items | output_items | route | route_completed | alternate_routes | alternate_routes_completed | alert
begin-case-1 | BEGIN | Begin case | [5 empty] | authorization-issuance-case-1 | Y
authorization-issuance-case-1 | ACTION | Authorization issued on November 9, 2018. | 2018-11-09 |  |  | Case application | Serious Harm associated with phase 1 cofferdam footprint and dewatering – 2417 m2 November 1, 2018 to July 15, 2019¦Serious Harm associated with phase 2 cofferdam footprint and dewatering – 1867 m2 July 15, 2019 to July 15 2020¦ Serious Harm associated with 1088 m2 of infill associated with moving the dam downstream¦Fourteen conditions relating to avoiding and mitigating serious harm¦Six contingency measures | monitoring-mitigation-report-process-case-1 | Y | monitoring-offsetting-report-process-case-1 | Y
monitoring-mitigation-report-process-case-1 | PROCESS | Monitoring and report for avoidance, mitigation | 2018-11-09 |  |  | Fourteen conditions relating to avoiding and mitigating serious harm |  | begin-monitoring-mitigation-report-case-1 | Y
begin-monitoring-mitigation-report-case-1 | BEGIN | Begin monitoring and report for avoidance, mitigation | 2018-11-09 |  |  |  |  | decision-monitoring-mitigation-report-case-1 | Y
decision-monitoring-mitigation-report-case-1 | DECISION | Decision for avoidance and mitigation monitoring report | [5 empty] | end-monitoring-mitigation-report-case-1 | N
end-monitoring-mitigation-report-case-1 | END | End monitoring and report for avoidance and mitigation | 2018-11-09 |  |  |  |  | end-case-1 | N
monitoring-offsetting-report-process-case-1 | PROCESS | Monitoring and report for offsetting | 2018-11-09 |  |  | Six contingency measures | Habitat enhancement - creating a Walleye spawning shoal (760m2) at an offsite location¦ Reinstating 1080m2 of habitat upstream of the dam¦ 5 criteria to assess the implementation and effectiveness of the measures | begin-monitoring-offsetting-report-case-1 | Y
begin-monitoring-offsetting-report-case-1 | BEGIN | Begin monitoring and report for offsetting | 2018-11-09 |  |  |  |  | offsetting-report-1-case-1 | Y | site-visit-case-1 | Y
site-visit-case-1 | ACTION | DFO site visit | 2019-10-29 |  |  |  |  | offsetting-report-1-case-1 | Y
offsetting-report-1-case-1 | INPUT | Completed interim report 1 on effectiveness |  | 2019-12-31 | Parks Canada |  | Interim offsetting report 1 | receive-offsetting-report-1-case-1 | Y
receive-offsetting-report-1-case-1 | DECISION | Offsetting interim report 2 received | 2019-11-29 | 2019-11-29 |  | Interim offsetting report 1 | Interim offsetting report 1 compliance verification | offsetting-report-2-case-1 | Y
offsetting-report-2-case-1 | INPUT | Completed interim report 2 on effectiveness |  | 2020-12-31 | Parks Canada |  | Interim offsetting report 2 | receive-offsetting-report-2-case-1 | Y
receive-offsetting-report-2-case-1 | DECISION | Offsetting interim report 2 received | 2020-12-22 | 2020-12-22 |  | Interim offsetting report 2 | Interim offsetting report 2 compliance verification | offsetting-report-3-case-1 | Y
offsetting-report-3-case-1 | INPUT | Final report on effectiveness |  | 2021-12-31 | Parks Canada |  | Final offsetting report | receive-offsetting-report-3-case-1 | N
receive-offsetting-report-3-case-1 | DECISION | Offsetting final report received |  |  |  | Final offsetting report | Final offsetting report compliance verification | decision-monitoring-offsetting-report-case-1 | N
decision-monitoring-offsetting-report-case-1 | DECISION | Decision for offsetting monitoring report |  |  |  | Interim offsetting report 1 compliance verification¦Interim offsetting report 2 compliance verification¦Final offsetting report compliance verification |  | end-monitoring-offsetting-report-case-1 | N
end-monitoring-offsetting-report-case-1 | END | End monitoring and report for offsetting | 2018-11-09 |  |  | Habitat enhancement - creating a Walleye spawning shoal (760m2) at an offsite location¦ Reinstating 1080m2 of habitat upstream of the dam¦ 5 criteria to assess the implementation and effectiveness of the measures |  | end-case-1 | N
end-case-1 | END | End case | 2018-11-09
Note on G4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on H4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on J4: Nghia Doan: Already exists (Y) or placeholder for future (N)
Note on K4: Nghia Doan: Additional states to be connected to
Note on L4: Nghia Doan: Already exists (Y) or placeholder for future (N)

## 2
identification | title | category | start_state
case-2 | PSPC (public works canada), Temiskaming Dam and Bridge Replacement | Medium | begin-case-2
identification | type | title | date | event | actors | input_items | output_items | route | route_completed | alternate_routes | alternate_routes_completed | alert
begin-case-2 | BEGIN | Begin case | [5 empty] | authorization-issuance-case-2 | Y
authorization-issuance-case-2 | ACTION | Authorization issued on June 5, 2015. | 2015-06-05 |  |  | Case application | Serious Harm assicated with temportrya consturciton activitiies¦Serious Harm associated with permanent habitat loss due to new footprint Downstream (1088m2)¦Minimum 2, maximum 5 offsetting reports depending on the interim reports¦14 conditions relating to avoiding and mitigating serious harm¦3 offsetting measures and 3 contingency measures | monitoring-report-mitigation-process-case-2 | Y | monitoring-report-offsetting-process-case-2 | Y
monitoring-report-mitigation-process-case-2 | PROCESS | Monitoring report for avoidance and mitigation | 2015-06-05 |  |  | 14 conditions relating to avoiding and mitigating serious harm |  | begin-monitoring-mitigation-report-case-2 | Y
begin-monitoring-mitigation-report-case-2 | BEGIN | Begin monitoring and report for avoidance and mitigation | 2015-06-05 |  |  |  |  | site-visit-case-2 | Y | mitigation-report-1-case-2 | Y
site-visit-case-2 | ACTION | DFO site visit | 2017-10-26 |  |  |  | Site visit compliance verification | mitigation-report-1-case-2 | Y
mitigation-report-1-case-2 | INPUT | Completed interim report 1 mitigation |  | 2016-01-31 | PWGSC |  | Interim mitigation report 1 | receive-mitigation-report-1-case-2 | Y
receive-mitigation-report-1-case-2 | DECISION | Received interim mitigation report 1 | 2016-03-29 |  |  | Interim mitigation report 1 | Interim mitigation report 1 received late | mitigation-report-2-case-2 | Y |  |  | Interim mitigation report 1 received late
mitigation-report-2-case-2 | INPUT | Completed interim mitigation report 2 on mitigation |  | 2017-01-31 | PWGSC |  | Interim mitigation report 2 | receive-mitigation-report-2-case-2 | Y
receive-mitigation-report-2-case-2 | DECISION | Received interim mitigation report 2 | 2017-04-06 |  |  | Interim mitigation report 2 | Interim mitigation report 2 received late | decision-monitoring-mitigation-report-case-2 | Y |  |  | Interim mitigation report 2 received late
decision-monitoring-mitigation-report-case-2 | DECISION | Decision for avoidance and mitigation monitoring report |  |  |  | Site visit compliance verification¦Interim mitigation report 1 received late¦Interim mitigation report 2 received late |  | end-monitoring-mitigation-report-case-2 | Y
end-monitoring-mitigation-report-case-2 | END | End monitoring and report for avoidance and mitigation | 2018-11-09 | 2017-03-15 |  |  |  | end-case-2 | Y
monitoring-report-offsetting-process-case-2 | PROCESS | Monitoring report for offsetting and dam operation | 2015-06-05 |  |  | 3 offsetting measures and 3 contingency measures |  | begin-monitoring-offsetting-report-case-2 | Y
begin-monitoring-offsetting-report-case-2 | BEGIN | Begin monitoring and report for offsetting and operation dam | 2015-06-05 |  |  |  |  | offsetting-report-1-case-2 | Y
offsetting-report-1-case-2 | INPUT | Completes interim offsetting report 1 |  | 2016-01-31 | PWGSC |  | Interim offsetting report 1 | receive-offsetting -report-1-case-2 | Y
receive-offsetting -report-1-case-2 | DECISION | Interim offsetting report 1 received |  |  |  | Interim offsetting report 1 | Interim offsetting report 1 not received | offsetting-report-2-case-2 | Y |  |  | Interim offsetting report 1 not received
offsetting-report-2-case-2 | INPUT | Interim offsetting report 2 |  | 2018-01-31 | PWGSC |  | Interim offsetting report 2 | receive-offsetting-report-2-case-2 | Y
receive-offsetting-report-2-case-2 | DECISION | Interim offsetting report 2r eceived | 2018-01-26 |  |  | Interim offsetting report 2 | Interim offsetting report 2 received late | offsetting-report-3-case-2 | Y |  |  | Interim offsetting report 2 received late
offsetting-report-3-case-2 | INPUT | Interim offsetting report 3 |  | 2019-01-31 | PWGSC |  | Interim offsetting report 3 | receive-offsetting-report-3-case-2 | Y
receive-offsetting-report-3-case-2 | DECISION | Report received |  |  |  | Interim offsetting report 3 | Interim offsetting report 3 not received | decision-monitoring-offsetting-report-case-2 | Y |  |  | Interim offsetting report 3 not received
decision-monitoring-offsetting-report-case-2 | DECISION | Decision for offsetting monitoring report |  |  |  | Interim offsetting report 1 not received¦Interim offsetting report 2 received late¦Interim offsetting report 3 not received | Input for authorization amendment | end-monitoring-offsetting-report-case-2 | Y
end-monitoring-offsetting-report-case-2 | END | End monitoring and report for offsetting and operation dam |  | 2017-03-15 |  |  |  | authorization-amendment-case-2 | Y
authorization-amendment-case-2 | ACTION | Authorization issued on October 25, 2019. | 2019-10-25 |  |  | Input for authorization amendment | Monitoring reports mus be completed
end-case-2 | END | End case
Note on G4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on H4: Nghia Doan: List of items, can be files, entries, documents, etc anything that needs tracking, monitoring, or add information to the working process. In case if it is a list, use the pipe “¦” character to separate the items.
Note on J4: Nghia Doan: Already exists (Y) or placeholder for future (N)
Note on K4: Nghia Doan: Additional states to be connected to
Note on L4: Nghia Doan: Already exists (Y) or placeholder for future (N)